**VIRGINIA MUSEUM OF NATURAL HISTORY**

**AAM Reaccreditation Calendar**

Winter 2023-2024 Review requirements

Accumulate documents

Update documents

Spring 2024 *ad hoc* AAM reaccreditation committee

begins review of submission template and finalized

documents

Summer 2024 Develop written narratives for template

Assembly of package for submission

Staff internal review of package

September 2024 Final review and recommendations by the

*ad hoc* AAM reaccreditation committee

1 November 2024 Reaccreditation package submission due date

~Spring 2025 Site visit by peer reviewers

~Summer 2025 Final decision by AAM reaccreditation commission

15 August 2025 Members’ Celebration to coincide with August BOT

Meeting

* Staff, Boards
* Members
* DOE staff
* Legislators