**VIRGINIA MUSEUM OF NATURAL HISTORY**

**AAM Reaccreditation Calendar**

Winter 2023-2024 Review requirements

Accumulate documents

 Update documents

Spring 2024 *ad hoc* AAM reaccreditation committee

 begins review of submission template and finalized

documents

Summer 2024 Develop written narratives for template

 Assembly of package for submission

 Staff internal review of package

September 2024 Final review and recommendations by the

 *ad hoc* AAM reaccreditation committee

1 November 2024 Reaccreditation package submission due date

~Spring 2025 Site visit by peer reviewers

~Summer 2025 Final decision by AAM reaccreditation commission

15 August 2025 Members’ Celebration to coincide with August BOT

Meeting

* Staff, Boards
* Members
* DOE staff
* Legislators